## PMP Questions
ID | Question ID | Question Text | Question Type | Options (JSON) | Correct Options (JSON) | Domain | Task | PM Approach | Explanation
1 | Q001 | Which of the following, once approved, does not require an approved change request to be modified? | select_one | [{"letter": "A", "text": "Policies or procedures in the project management plan"}, {"letter": "B", "text": "Contract terms"}, {"letter": "C", "text": "Cost, scope, or schedule baselines"}, {"letter": "D", "text": "Project charter"}] | {"answer": "D"} | 2. Process | 2.10 Manage project changes | Predictive | This question is tricky and counter-intuitive because the project charter once completed and signed typically does not change except under very unusual circumstances; for example, the change of a project sponsor or project manager mid-project, both of which are rare occurrences. In those instances, however, typically an addendum is added to the project charter rather than a change made to the charter. The addition reflects the change, and all project stakeholders should be informed. Before signature, the project charter can and will change, but these changes do not require change control procedures either as the charter is not final until it is signed. A change request is required to modify formally controlled project documents, typically the components of the project management plan. Table 4-1. Project Management Plan and Project Documents, specifies the list of the components of the project management plan as well as project documents. Unless stated otherwise in the scenario, the components of the project management plan require a change request to be modified, while an update to the project documents does not require a change request. Since the project charter is not a component of the project management plan, a change request is not required to modify the project charter.
2 | Q002 | A plan-driven project has many deliverables planned to be released at the end of the phase. The project manager wants to ensure that the deliverables are completed as expected. Which agile practices can the project manager recommend to the team to make certain that the deliverables are completed and delivered as expected? | select_one | [{"letter": "A", "text": "Definition of ready and iteration reviews"}, {"letter": "B", "text": "User stories and confidence votes"}, {"letter": "C", "text": "Definition of done and demonstrations"}, {"letter": "D", "text": "Backlog refinement and retrospectives"}] | {"answer": "C"} | 2. Process | 2.17 Plan and manage project/phase closure or transitions | Agile / Hybrid | To properly close a project phase or project, appropriate stakeholders sign off that work has been delivered. Techniques in agile project management methodologies such as "definition of done" and "demonstrations" can also be applied in a plan-driven project. This approach helps ensure that stakeholders agree at the start of the project that the work is not only completed, but a shared understanding of done and the criteria to accept the work are exactly defined. Demonstrations serve as checkpoints throughout the project to demonstrate product increments to the relevant stakeholders, get feedback, and adjust as needed. By utilizing those two agile practices, project teams can better determine whether or not the project or phase can be successfully closed. ADefinition of ready and iteration reviews
3 | Q003 | In traditional project management, the term for frequent changes in scope, is called 'scope creep'. In agile project management, what is true of frequent changes in scope? | select_one | [{"letter": "A", "text": "It does not exist because the scope is defined upfront"}, {"letter": "B", "text": "It is expected and accepted because the requirements are unknown upfront and change regularly"}, {"letter": "C", "text": "It is expected because the scope and requirements often change during the execution of agile projects"}, {"letter": "D", "text": "It is expected and managed using agile change control management system"}] | {"answer": "C"} | 2. Process | 2.10 Manage project changes | Agile / Hybrid | In their book, The Software Project Manager's Bridge to Agility, Michele Sliger and Stacia Broderick state: "Changes to the scope in agile projects are handled through the utilization of a prioritized product backlog. Adding or reprioritizing a feature in the product backlog constitutes what in traditional project management is known as scope change, or 'scope creep'". In agile terminology, however, it is called 'expected change'. One of the twelve guiding agile principles mentions that changes are welcomed, even late in development. Agile processes harness change for the customer's competitive advantage and to meet the changing needs of the customers.
4 | Q004 | The project you are leading is supposed to upgrade the application developed by your company on desktop computers and mobile devices. Last week, a major supplier of electronics unexpectedly released a new mobile device. You realize that your application, with a little bit of modification, can run much faster and more securely on the new device. What should you do next in regards to this opportunity? | select_one | [{"letter": "A", "text": "Create a cost forecast and communicate it to stakeholders"}, {"letter": "B", "text": "Submit a change request to modify the application"}, {"letter": "C", "text": "Update project funding requirements in consideration for the unexpected work"}, {"letter": "D", "text": "Conduct variance analysis for an appropriate reserve amount"}] | {"answer": "B"} | 3. Business Environment | 3.3 Evaluate and address external business environment changes for impact on scope | Predictive | In this question, an unexpected opportunity presents itself. The modification of the application to be upgraded on the new mobile device could have a significant impact on multiple project constraints, including project scope, schedule, cost, quality, communications, risk, etc. Therefore, a change request should be submitted and analyzed first before any decision is made. The change request will have to go thru the organization's change control process established for the project. ACreate a cost forecast and communicate it to stakeholders
5 | Q005 | A company operating in a high-tech industry with new technologies emerging every few months charters a project that is expected to have unstable requirements for its whole duration. A project manager is assigned, and the sponsor requests the project manager to suggest a strategy that best supports the adaptability and resiliency of the project in this environment. Which of the following capabilities should the project leader leverage for this strategy? | select_one | [{"letter": "A", "text": "Expediting decision making to occur at the first possible moment"}, {"letter": "B", "text": "Acquiring project team members with a highly specialized set of skills"}, {"letter": "C", "text": "Limiting the exposure to tacit knowledge and leveraging explicit knowledge"}, {"letter": "D", "text": "Incorporating short feedback loops to adapt the product and process quickly"}] | {"answer": "D"} | 2. Process | 2.13 Determine appropriate project methodology/methods and practices | Agile / Hybrid | Project leaders should embrace adaptability and resiliency. Adaptability refers to the ability to respond to changing conditions, while resiliency is the ability to absorb impacts and recover quickly from a setback or failure. In the scenario, the organization operates in the high-tech industry with new technologies emerging every few months, and the project is expected to have unstable requirements for its entire duration. Adaptive (agile) methodologies are best suited to projects with unstable requirements. A predictive framework typically requires the project to be planned in detail upfront, and changes are tightly controlled. Thus, a predictive framework works well when the requirements are well understood up front and are not likely to change. Conversely, an iterative and incremental life cycle incorporates planning, execution, and feedback within each iteration permitting the requirements and deliverables to be progressively elaborated. Short feedback loops are a fundamental component of agile projects. Integrating short feedback loops into the project workflow enhances adaptability and resiliency by ensuring that the project team can collect fast and frequent feedback from relevant stakeholders and increases the opportunities to adapt to emerging technologies and changes. AExpediting decision making to occur at the first possible moment
6 | Q006 | To better use existing knowledge and to create new knowledge for a project, the project manager is looking for ways to identify any knowledge gaps. Which of the following would help the project manager the most to complete this process? | select_one | [{"letter": "A", "text": "Bid documents"}, {"letter": "B", "text": "Resource breakdown structure"}, {"letter": "C", "text": "Quality metrics"}, {"letter": "D", "text": "To-complete performance index"}] | {"answer": "B"} | 1. People | 1.5 Ensure team members/stakeholders are adequately trained | Predictive | Using existing knowledge and creating new knowledge for a project is essentially the definition of the Manage Project Knowledge process. When the knowledge that the project has is compared to its knowledge needs, then the gaps in knowledge can be identified and addressed. Specifically, the resource breakdown structure, as it pertains to the Manage Project Knowledge process, includes information on the composition of the team and may help to understand what knowledge is available as a group and what knowledge may be missing. BResource breakdown structure
7 | Q007 | A PMO steeped in traditional waterfall project management has hired you, as an agile practitioner, to guide the organization's transformation to agile. After completing an initial assessment of the organizational culture, you have realized that many of the stakeholders are resistant to the change. What is your best course of action? | select_one | [{"letter": "A", "text": "Provide training to ensure the employees are more highly specialized"}, {"letter": "B", "text": "Transition all projects to agile at the same time"}, {"letter": "C", "text": "Seek a high-level executive willing to champion the cause"}, {"letter": "D", "text": "Ensure the work is decomposed into silos"}] | {"answer": "C"} | 3. Business Environment | 3.4 Support organizational change | Agile / Hybrid | Transitioning an organization from traditional project management to an agile approach can be very challenging as it will likely involve significant organizational and cultural change and may take years to accomplish. For example, a functional organizational type that is structured in silos may need to undergo a major restructuring to adopt a matrix organizational structure to support cross-functional teams. The organization may at first opt to gradually transition from waterfall to hybrid and finally to an agile approach. Alternatively, the organization may want to stop at the hybrid stage, thus benefitting from both worlds, assuming the hybrid project management approach will meet the needs of the future projects undertaken by the organization. In any case, executive management's willingness to change will be a significant factor in the transition from waterfall to hybrid to agile. Visible and active executive sponsorship will be crucial to support the significant changes that will be required for the transition to successful. The incorrect answer choices all represent agile antipatterns. AProvide training to ensure the employees are more highly specialized
8 | Q008 | A PMO steeped in traditional waterfall project management has hired you, as an agile practitioner, to guide the organization's transformation to agile. After completing an initial assessment of the organizational culture, you have realized that many of the stakeholders are resistant to the change. What is your best course of action? | select_one | [{"letter": "A", "text": "Provide training to ensure the employees are more highly specialized"}, {"letter": "B", "text": "Transition all projects to agile at the same time"}, {"letter": "C", "text": "Seek a high-level executive willing to champion the cause"}, {"letter": "D", "text": "Ensure the work is decomposed into silos"}] | {"answer": "C"} | 3. Business Environment | 3.4 Support organizational change | Agile / Hybrid | Transitioning an organization from traditional project management to an agile approach can be very challenging as it will likely involve significant organizational and cultural change and may take years to accomplish. For example, a functional organizational type that is structured in silos may need to undergo a major restructuring to adopt a matrix organizational structure to support cross-functional teams. The organization may at first opt to gradually transition from waterfall to hybrid and finally to an agile approach. Alternatively, the organization may want to stop at the hybrid stage, thus benefitting from both worlds, assuming the hybrid project management approach will meet the needs of the future projects undertaken by the organization. In any case, executive management's willingness to change will be a significant factor in the transition from waterfall to hybrid to agile. Visible and active executive sponsorship will be crucial to support the significant changes that will be required for the transition to successful. The incorrect answer choices all represent agile antipatterns. AProvide training to ensure the employees are more highly specialized
9 | Q009 | Midway into project execution, a supplier notifies the project manager that the roof over their manufacturing plant has collapsed due to a tornado. The supplier wants to terminate the contract citing the 'Act of God' clause in the contract. The procurement department confirms the clause is indeed in the contract. What should the project manager do next? | select_one | [{"letter": "A", "text": "Close the procurement with the supplier"}, {"letter": "B", "text": "Begin the process of claims administration"}, {"letter": "C", "text": "Insist the supplier delivers on the contract"}, {"letter": "D", "text": "Consult with the project sponsor"}] | {"answer": "A"} | 2. Process | 2.11 Plan and manage procurement | Predictive | Vendor contracts typically contain a force majeure clause, sometimes referred to as an 'Act of God clause', which provides a defense mechanism against breach of contract for circumstances beyond human control such as natural disasters. The reason for terminating the contract provided by the vendor appears to meet the definition of a force majeure clause, which has been confirmed by the procurement department. Hence, the vendor is within their legal right to terminate the contract. The project manager should close the procurement and focus on finding another qualified vendor to supply the required parts. AClose the procurement with the supplier
10 | Q010 | A major project deliverable has been completed and transitioned to operations. The project team is ready to move on to the next deliverable scheduled. One team member speaks up and asks if the team should conduct a retrospective. What is the project manager's best response? | select_one | [{"letter": "A", "text": "Yes, whenever any part of the project closes, the team can conduct a retrospective."}, {"letter": "B", "text": "No, the retrospectives are held only after the project is closed."}, {"letter": "C", "text": "Yes, but at the end of the project phase when we review the other deliverables."}, {"letter": "D", "text": "No, retrospectives are only for agile chartered projects."}] | {"answer": "A"} | 2. Process | 2.17 Plan and manage project/phase closure or transitions | Predictive | A retrospective is a scheduled review to record lessons that have been learned during the process of producing the project deliverables. Retrospectives are a valuable tool and technique of closing any key time in the project - an iteration, phase, deliverable, milestone, or even the project as a whole. These sessions are conducted as needed to help the project team learn from their work, processes, and the project management practices. These lessons learned can be applied to the future work of this project, as well as other projects. Therefore, of the choices provided, responding to the team member that a retrospective should be conducted and it can be held whenever any part of the project closes is the best answer to the question asked. AYes, whenever any part of the project closes, the team can conduct a retrospective.
11 | Q011 | A project manager has taken over a project that has been in execution for a few months. He ran into problems right away. He has had difficulty getting sign off on decisions; he doesn't have the authority to acquire the equipment necessary for the project; the stakeholders and the project team have differing opinions about the objectives and the outcome of the project. What is the most likely source of these problems? | select_one | [{"letter": "A", "text": "Weak leadership skills"}, {"letter": "B", "text": "Lack of a project charter"}, {"letter": "C", "text": "Lack of a project management plan"}, {"letter": "D", "text": "Lack of a procurement management plan"}] | {"answer": "B"} | 1. People | 1.2 Lead a team | Predictive | A project charter is the document that authorizes the existence of a project and provides the project manager with the authority to apply organizational resources to project activities. The project charter also states the purpose, primary objectives, vision, and mission for the project, aligning the project stakeholders and the project team with the project goals, expectations, and outcomes. A project sponsor approves the project charter and is supposed to provide support for the project manager to achieve the project goals. While other answer choices could have been the source of 'some' of the project manager's problems, the lack of a project charter addresses all of the project manager's problems and is, therefore, the best answer to the question asked. AWeak leadership skills
12 | Q012 | A project manager is near the end of a large and complex project, which required the services of several different vendors. Currently, the project manager is about to start the process of finalizing all activities for project closure. What should the project manager do first? | select_one | [{"letter": "A", "text": "Submit a change request to update the project management plan"}, {"letter": "B", "text": "Update all applicable project documents and mark them as final versions"}, {"letter": "C", "text": "Revise and finalize the business case and the project charter"}, {"letter": "D", "text": "Begin the alternative dispute resolution procedure with the vendors"}] | {"answer": "B"} | 2. Process | 2.17 Plan and manage project/phase closure or transitions | Predictive | The question suggests that the Close Project or Phase process is underway. Only one answer choice represents activities that are performed as part of the Close Project or Phase process which include finalizing the project documents. All project documents may be updated and marked as final versions as a result of project closure. Based on the scenario described, the project manager is about to start the process of finalizing all activities for project closure. Therefore, of the options provided, updating all applicable project documents and marking them as final versions makes the more sense for the project manager to do, making this action the best answer to the question asked. ASubmit a change request to update the project management plan
13 | Q013 | After completing eight iterations, the team realizes the mistakes they made in the first iteration. What is the next best action for the project team to do? | select_one | [{"letter": "A", "text": "Proceed to the next iteration as planned"}, {"letter": "B", "text": "Update the lessons learned repository"}, {"letter": "C", "text": "Apply the lesson learned to the next iteration"}, {"letter": "D", "text": "Restart the first iteration"}] | {"answer": "C"} | 2. Process | 2.13 Determine appropriate project methodology/methods and practices | Agile / Hybrid | The scenario is designed around the Manage Project Knowledge process which is the process of using existing knowledge and creating new knowledge to achieve the project's objectives and contribute to organizational learning. Managing the vast amount of project knowledge and the lessons that are constantly learned by all project stakeholders throughout the project enables the project team to leverage that knowledge and apply it. Applying lessons learned and project knowledge supports the project organization, the project outcomes, and operation of the current and future projects. Documenting the knowledge into a lesson learned register is one method of capturing that knowledge to ensure it is not lost. Applying that knowledge to the project is even more beneficial. There is a misconception that projects must wait until the end of a project in order to document it. Just accepting mistakes happened is not enough. Knowledge is fluid and best shared and used at the point it is most needed. AProceed to the next iteration as planned
14 | Q014 | After reviewing comments from a participant survey from a project kick-off meeting, it is clear that more frequent breaks would have helped the participants maintain focus throughout the meeting. Where should this information be captured? | select_one | [{"letter": "A", "text": "The kick-off meeting is over, so this information is no longer relevant"}, {"letter": "B", "text": "Stakeholder register"}, {"letter": "C", "text": "Lessons learned register"}, {"letter": "D", "text": "Lessons learned repository"}] | {"answer": "C"} | 2. Process | 2.16 Ensure knowledge transfer for project continuity | Predictive | Surveys are a popular method of gathering valuable feedback from meeting participants, which can be used to improve the effectiveness of future meetings. The lessons learned gained from the feedback should be captured in the lessons learned register. The lessons learned register is a project document used to record knowledge gained during a project so that it can be used in the current project. During the Close Project or Phase process, the lessons learned register is archived as an organizational process asset for use on future projects. Therefore, of the choices given, capturing the feedback in the lessons learned register is the best answer to the question asked. AThe kick-off meeting is over, so this information is no longer relevant
15 | Q015 | A project team is installing new workstations across all its office locations. The team notices a lack of communication and coordination, which affects their ability to plan support resources effectively and creates frustration. What action should the project manager take first? | select_one | [{"letter": "A", "text": "Organize a conflict resolution meeting encouraging each team member to discuss concerns and listen to each other's viewpoints."}, {"letter": "B", "text": "Suggest a more integrated approach to create a scalable, cost-effective setup."}, {"letter": "C", "text": "Address the team, stressing the importance of collaboration and reminding them of their common goal."}, {"letter": "D", "text": "Propose regular updates and coordinate meetings, ensuring all team members are kept in the loop."}] | {"answer": "C"} | 1. People | 1.2 Lead a team | Predictive | Before a conflict resolution meeting, the project manager would want to understand and assess any root causes of conflict or lack of communication. Conflict resolution meetings would be something to consider in another step in the process. Suggesting a more integrated approach to creating a scalable and cost-effective setup is a logical step in resolving technical conflicts within a project team. Jumping straight to suggesting technical solutions without addressing the underlying interpersonal issues and conflicts can result in superficial resolutions that do not address the root causes of the discord.
16 | Q016 | A project manager must determine the execution strategy for a government-funded infrastructure project with significant financial constraints. The project requires coordination between multiple contractors, fixed budgets, and a phased rollout to mitigate risks. Which execution strategy should the project manager recommend? | select_one | [{"letter": "A", "text": "Agile execution with frequent iterations"}, {"letter": "B", "text": "Predictive execution with phased contracting"}, {"letter": "C", "text": "Incremental execution with rolling wave planning"}, {"letter": "D", "text": "Hybrid execution using Agile and Predictive elements"}] | {"answer": "B"} | 2. Process | 2.13 Determine appropriate project methodology/methods and practices | Predictive | The correct answer is B) Predictive execution with phased contracting. Predictive strategies provide clear plans and control, while phased contracting addresses financial constraints and coordination requirements. A government-funded infrastructure project with financial constraints, multiple contractors, and a phased rollout requires an execution strategy that ensures control, predictability, and structured coordination. Given these constraints, the predictive execution with phased contracting is the most suitable approach because:
17 | Q017 | Which of the following would be one of the last tasks for a project manager to perform as part of the administrative closure of a project? | select_one | [{"letter": "A", "text": "Obtaining formal acceptance of the project deliverables"}, {"letter": "B", "text": "Conducting earned value analysis"}, {"letter": "C", "text": "Evaluating stakeholder satisfaction with the project"}, {"letter": "D", "text": "Verifying the correctness of the deliverables"}] | {"answer": "C"} | 2. Process | 2.17 Plan and manage project/phase closure or transitions | Predictive | A project is considered a success when the project objectives have been achieved. One important objective established early in the project's planning is stakeholder satisfaction. Stakeholder satisfaction should be monitored throughout the project and finally used as a measure of project success at the end of the project. The question surrounds the administrative closure of a project implying the answer choice should be one of the activities carried out during the Close Project or Phase process. One of the last tasks of the project manager during this process is measuring stakeholder satisfaction for the project as a whole. AObtaining formal acceptance of the project deliverables
18 | Q018 | You are managing a big project. To direct, manage, monitor and control your project work more efficiently, you want the project key performance indicators to be gathered and reported automatically. What is the best tool to use for this purpose? | select_one | [{"letter": "A", "text": "Project management information system"}, {"letter": "B", "text": "Published estimating data"}, {"letter": "C", "text": "Communication technology"}, {"letter": "D", "text": "Performance reviews"}] | {"answer": "A"} | 2. Process | 2.9 Integrate project planning activities | Predictive | A project management information system is an enterprise environmental factor. The system can be used as a tool or technique of, or serve as an input to, many project management processes. The project management information system consists of the tools and techniques used to gather, integrate, and disseminate the outputs of project management processes. The system is used to support all aspects of the project from initiating through closing, for example providing access to tools such as a scheduling tool, a work authorization system, a configuration management system, an information collection and distribution system, or interface to other online automated systems. The project management information system can include both manual and automated systems. One of its capabilities is to automatically gather and report on key performance indicators which is what the question asks. Therefore, a project management information system is the best answer to the question. AProject management information system
19 | Q019 | A vendor has been awarded a contract to develop a software module for a customer who develops a new banking application. The development team of the vendor is accustomed to agile methods, but the contract with the customer requires that the module be developed using a waterfall framework. What should the vendor's project leader do? | select_one | [{"letter": "A", "text": "Use an incremental and iterative approach for the software development but deliver the module in a single release"}, {"letter": "B", "text": "Gather all requirements upfront and ensure that no changes are made throughout the course of the project"}, {"letter": "C", "text": "Use a predictive approach as specified in the contract and avoid all practices associated with agile development"}, {"letter": "D", "text": "To the extent contractually permitted, incorporate as many agile best practices as appropriate for the project"}] | {"answer": "D"} | 2. Process | 2.13 Determine appropriate project methodology/methods and practices | Agile / Hybrid | Project leaders should tailor projects based on context. In this scenario, the project will operate within the bounds of a predictive framework. However, the project team for the performing organization should take advantage of their agile skillset to the greatest extent permitted under the contract terms, which will help the team maximize the delivery of business value. Some agile best practices are agnostic as to the overarching development approach. For example, the project leader could set up a war room for the development team to complete the work packages in the WBS, which would enhance collaboration. Another example would be to schedule daily standup meetings to help the developers coordinate their activities for the day and surface any impediments. These are just two examples of agile best practices that could be incorporated into the project without violating the requirement for the use of a predictive framework. AUse an incremental and iterative approach for the software development but deliver the module in a single release
20 | Q020 | During the last few iterations of the agile project, the team members found themselves with many partially completed user stories. One team member suggested imposing an upper limit on the amount of work that the team takes on at any point during an iteration. What should an agile practitioner advise in this situation? | select_one | [{"letter": "A", "text": "The team should not set an upper limit on the work in progress because that would reduce the team's velocity."}, {"letter": "B", "text": "The team should set an upper limit on the work in progress to reduce waste."}, {"letter": "C", "text": "Consult the customer before setting an upper limit on the work in progress as the project goal is to add value to the customer."}, {"letter": "D", "text": "Only the sponsor can approve limits that lower resource utilization and may lead to wasting project funds."}] | {"answer": "B"} | 2. Process | 2.8 Plan and manage scope | Agile / Hybrid | Work in progress (WIP) limits are part of the Kanban development system. By putting such a limit, agile teams ensure that the project's throughput increases, as partially completed work, which is considered waste, does not stay in the system. Having limits on WIP also reduces the cycle time to deliver completed work. AThe team should not set an upper limit on the work in progress because that would reduce the team's velocity.
21 | Q021 | The current sprint's goal is to develop subcomponents that will be integrated into functional deliverables. Due to the highly specialized nature of the subcomponents, each team member will have to complete their development tasks individually. Despite this, the project leader wants to ensure that the activities among the team members are properly coordinated. What is the best course of action for the project leader? | select_one | [{"letter": "A", "text": "During sprint planning, review the interdependencies between the development tasks on the project schedule network diagram"}, {"letter": "B", "text": "Ask for the team members' improvement suggestions while transferring the knowledge gained to the lessons learned repository"}, {"letter": "C", "text": "Ensure that changes to the subcomponents are approved by the CCB to strengthen their alignment with the functional deliverables"}, {"letter": "D", "text": "Encourage the project team members to actively participate in the discussions that take place during the daily standup meetings"}] | {"answer": "D"} | 3. Business Environment | 3.2 Evaluate and deliver project benefits and value | Agile / Hybrid | Systems thinking requires that project leaders and teams recognize, evaluate, and respond to system interactions. Projects may have subsystems, and project deliverables can have subcomponents. Ideally, agile project team members will collaborate in real-time to produce the deliverables for each iteration. However, the scenario describes a situation in which the highly specialized nature of the subcomponents makes real-time collaboration unrealistic, forcing the team members to perform their work individually. These circumstances elevate the importance of participation in the daily standup meetings to even a higher degree. The daily standup meeting is a brief collaboration meeting in which the team reviews progress from the previous day, states intentions for the current day, and highlights any impediments. Under the circumstances provided in this scenario, this daily meeting might be the project team members' only opportunity to coordinate their activities to ensure that each subcomponent can be integrated into a functional deliverable later in the project. ADuring sprint planning, review the interdependencies between the development tasks on the project schedule network diagram
22 | Q022 | You are attending a meeting where the project manager, sponsor, vendors, and several other stakeholders are capturing lessons learned. The attendees are in a celebratory mood, the sponsor is happy, and the vendors are asking if there is the potential for any follow-on work. What type of meeting are you attending? | select_one | [{"letter": "A", "text": "Team building meeting"}, {"letter": "B", "text": "Project kick-off meeting"}, {"letter": "C", "text": "Project retrospective"}, {"letter": "D", "text": "Bidder conference"}] | {"answer": "C"} | 2. Process | 2.17 Plan and manage project/phase closure or transitions | Predictive | A project retrospective is a meeting held during project closure to record lessons learned during the project and transfer the information captured in the lessons learned register to the lessons learned repository, where it can be used to improve the performance of future projects. Since the project has concluded, the atmosphere is likely to be celebratory, especially if the project was a success. Additionally, it is not surprising that vendors, who just had their contracts closed, could be inquiring about follow-on work during such a meeting. Note that the question describes three different meetings including a lessons learned meeting (retrospective), a celebration meeting, and a customer wrap-up meeting. However, these meetings can be held independently or in combination. Since the scenario implies that the meeting is occurring as part of project closure, the project retrospective is the best answer to the question asked. The incorrect responses would not likely occur at the end of the project and be celebratory in nature.
23 | Q023 | A project has uncertain requirements that will evolve as the project unfolds. Project funding is also unclear since the organization does not want to invest money in a poorly-defined product. Regardless, even with such a high degree of uncertainty, the project team has been required to deliver the first working product increment in two weeks. What development approach should the project manager recommend for this project? | select_one | [{"letter": "A", "text": "Predictive"}, {"letter": "B", "text": "Hybrid"}, {"letter": "C", "text": "Uncertain"}, {"letter": "D", "text": "Adaptive"}] | {"answer": "D"} | 2. Process | 2.13 Determine appropriate project methodology/methods and practices | Agile / Hybrid | A development approach refers to the means used to create and evolve the product, service, or result during the project life cycle. The selection of the development approach depends on multiple variables, such as the product, project, and organization. Requirements certainty is an example of the product variable. When requirements are uncertain and are expected to evolve as the project unfolds, an adaptive development approach should be recommended. Funding availability is an example of the project variable. Projects that work in an environment of funding uncertainty can benefit from an adaptive approach. The need to deliver early, even if it's not a finished product, is a schedule constraint, which is another example of the project variable that would favor an adaptive approach. With the above variables matching those described in the scenario, recommending the adaptive development approach for the project would make the most sense for the project manager.
24 | Q024 | An agile team has to implement a new payroll system. The product owner is a payroll expert but is not familiar with agile planning. What advice should an agile coach offer to the product owner? | select_one | [{"letter": "A", "text": "Create an environment that facilitates face-to-face planning events involving relevant project stakeholders"}, {"letter": "B", "text": "Generate a requirements document for the team to develop the product exactly per customer specifications"}, {"letter": "C", "text": "Draft a project plan and send it to stakeholders for approval to ensure everybody are on the same page"}, {"letter": "D", "text": "Develop a Gantt chart listing project deliverables to get necessary resources from the project sponsor"}] | {"answer": "A"} | 2. Process | 2.1 Execute project with the urgency required to deliver business value | Agile / Hybrid | Agile encourages the creation of an environment that facilitates face-to-face planning events with stakeholders, customers, and team members. Having a dedicated space for the team collaboration makes planning activities visible and transparent. An agile coach would need to mentor the product owner on agile adaptive planning techniques. The product owner should make time to be available to the team, provide feedback, and any information in order for the team to move forward. The plan will be evolving, and the product owner will be grooming the backlog frequently as changes are coming. Information radiators are invaluable tools for stakeholders to view project progress. ACreate an environment that facilitates face-to-face planning events involving relevant project stakeholders
25 | Q025 | A business case with a proposal for a project has been submitted to the company's portfolio steering committee. The committee approves the proposal and requests one of the company's project managers to lead the project. What should the project manager do next? | select_one | [{"letter": "A", "text": "Meet with the sponsor and key stakeholders to learn the key project elements"}, {"letter": "B", "text": "Develop the project management plan"}, {"letter": "C", "text": "Determine how to plan for each Project Management Knowledge Area"}, {"letter": "D", "text": "Create the project scope statement"}] | {"answer": "A"} | 2. Process | 2.11 Plan and manage procurement | Predictive | A business case is defined as a documented economic feasibility study used to establish the validity of the benefits of a selected component lacking sufficient definition and that is used as a basis for the authorization of further project management activities. An approved business case serves as an input to the Develop Project Charter process which is the next logical step for the project manager in the scenario described. However, having an approved business case is not enough to complete this process. Key project elements and high-level information should be identified to accomplish this goal. This can be achieved by using tools and techniques applicable to the Develop Project Charter process. Data gathering and expert judgment are among those tools and techniques. Meeting with the sponsor, key stakeholders, and other subject matter experts to learn the key project elements from their perspective are examples of data gathering and expert judgment. Therefore, of the choices provided, meeting with these groups and individuals is what the project manager should do next. AMeet with the sponsor and key stakeholders to learn the key project elements
26 | Q026 | The deliverables of a two-year-long project have just been accepted. It is four months late, but the customer is pleased to have it. The project manager is glad to be done with the deliverables but is concerned about the cost and schedule overruns. He decides to re-run the initial cost-benefit analysis using the actual project costs. Where should the project manager obtain the initial cost-benefit analysis? | select_one | [{"letter": "A", "text": "From the customer"}, {"letter": "B", "text": "The project charter"}, {"letter": "C", "text": "The business case"}, {"letter": "D", "text": "The benefits management plan"}] | {"answer": "C"} | 3. Business Environment | 3.2 Evaluate and deliver project benefits and value | Predictive | A business case contains a documented economic feasibility study used to establish the validity of the benefits of a selected component lacking sufficient definition, and that is used as a basis for the authorization of further project management activities. The business case has a complete cost-benefit analysis for the project. It can provide the project manager with all the initial information used to justify the project, allowing the project manager to re-run the cost-benefit analysis substituting the initial costs with the actual costs. AFrom the customer
27 | Q027 | The latest software released to the customer in the first project phase is full of defects. The customer is angry and demands that the development of the new release, which is planned to be delivered in the second phase, is much more transparent. The customer wants to see the team’s results more regularly and without very long development intervals in-between. Which of the following could the project team introduce in the second phase to better comply with the customer's demand? (Choose four.) | select_multiple | [{"letter": "A", "text": "A cadence with regular timeboxes"}, {"letter": "B", "text": "Regular and frequent retrospectives"}, {"letter": "C", "text": "Optimization at the level of each individual team member"}, {"letter": "D", "text": "Test-driven development practices"}, {"letter": "E", "text": "Incremental delivery using a backlog"}, {"letter": "F", "text": "Limiting the number of changes before the software is released"}] | {"answers": ["A"]} | 2. Process | 2.1 Execute project with the urgency required to deliver business value | Agile / Hybrid | The scenario implies that the first phase of the project was likely delivered using a waterfall project management approach, where the software had been developed in one long iteration and deployed at the customer site. This approach, especially with software development products, often results in more defects in comparison to the iterative and incremental approach. What customer demands for the second phase can be achieved by incorporating agile practices, making the second phase hybrid. For many project teams who need to introduce more agility, setting up regular timeboxes and frequent retrospectives help organize the team's work in close collaboration with the customer. In addition to a more iterative approach, an incremental delivery using a backlog is another good first step towards agility in a project. According to the scenario, the team has problems with poor quality – test-driven development practices can address that. AA cadence with regular timeboxes
28 | Q028 | During project execution, significant volumes of work performance data are being generated. The project manager wishes to select some of this data to be reviewed and analyzed in the controlling processes to assess project performance. Which of the following examples of work performance data is the project manager most likely to select for such an analysis? | select_one | [{"letter": "A", "text": "The number of the project team members"}, {"letter": "B", "text": "Story points completed"}, {"letter": "C", "text": "Estimated activity durations"}, {"letter": "D", "text": "Planned costs"}] | {"answer": "B"} | 2. Process | 2.9 Integrate project planning activities | Predictive | To answer this question properly, one needs to understand what is considered work performance data. Work performance data are the raw observations and measurements identified during activities being performed to carry out the project work. This data is generated during project execution and feeds or flows into various controlling processes. The controlling processes compare the work performance data with the established project baselines to assess project performance. Information available or developed during project planning is not considered work performance data. Examples of work performance data include work completed, key performance indicators, technical performance measures, actual start and finish dates of schedule activities, story points completed, deliverables status, etc. Of the choices provided, only story points completed qualifies as work performance data. AThe number of the project team members
29 | Q029 | The project charter for a project in the initiation stage provides an initial budget estimate of $1,000,000. The project will take four years to complete, and the revenues will be realized at the end of the project when the property is sold at the anticipated selling price of $1,100,000. You are of the opinion that the project should proceed since it is profitable, but the director of finance disagrees. What might have you done wrong? | select_one | [{"letter": "A", "text": "Neglected opportunity costs in the calculation"}, {"letter": "B", "text": "Did not account for project risk"}, {"letter": "C", "text": "Used nominal dollars instead of net present value (NPV)"}, {"letter": "D", "text": "Failed to account for sunk costs"}] | {"answer": "C"} | 3. Business Environment | 3.2 Evaluate and deliver project benefits and value | Predictive | The question indicates that costs will be incurred throughout the project, but the revenue will only be received at the end of the four-year-long project. The anticipated nominal selling price of $1,100,000 does not take into account the effect of inflation over the four-year period of the project. Using net present value (NPV) adjusts for inflation to get a more accurate assessment of the true value of future revenues. If the majority of the expense is incurred up front, then even a modest inflation rate of 3% could make the project unprofitable in terms of real value. Had you, as the project manager, used NPV in your calculation for net profit instead of nominal dollars, you would not have advocated for the project based on an anticipated profit of $100,000. The incorrect answer choices are all viable options for mistakes that may have been made, but there is no information from the description provided by the question to indicate such one way or another. Therefore, of the available choices, the only clear mistake that was made was the use of nominal dollars instead of NPV. The topic of this question is only briefly covered in thePMBOK®Guide. However, the Project Management Professional (PMP)®Examination Content Outline (ECO) indicates that while there are some commonalities between thePMBOK®Guideand the ECO, the exam is not bound by thePMBOK®Guide. The list of enablers specified in the tasks of the ECO domains is not exhaustive either. The ECO assumes that prospective PMP aspirants are familiar with other sources of information/preparation, including but not limited to the PMI Code of Ethics and Professional Conduct, PMI's Practice Standards (e.g., Scheduling, Earned Value Management, etc.), commonly frowned upon project management practices, such as gold plating, and others. We intentionally have these questions in our simulator so that you would be better prepared for the real exam. PMP aspirants are encouraged to explore additional sources of information and/or to be familiar with them from their project management experience.
30 | Q030 | During a project closure meeting, a stakeholder makes a suggestion that would improve the functionality of a vendor's deliverable. The suggestion does not get the attention of the participants and is quickly dropped without further action. What is the most likely reason for the suggestion being dropped? | select_one | [{"letter": "A", "text": "Suggestions are not allowed during project closure."}, {"letter": "B", "text": "The project team has already been released."}, {"letter": "C", "text": "Stakeholder influence during project closure is low."}, {"letter": "D", "text": "The deliverable still needs to be accepted."}] | {"answer": "C"} | 2. Process | 2.4 Engage stakeholders | Predictive | The question implies that the Close Project or Phase process is being performed. With project closure underway, the deliverable produced by the vendor would have already been formally accepted. During project closure, stakeholders have little, if any, influence over project deliverables. Stakeholders' ability to control the outcome of the project is lowest towards the end of the project because most of the work has already been completed. Therefore, of the available options, low stakeholder influence is the best response. ASuggestions are not allowed during project closure.
31 | Q031 | A project is plagued by various issues, such as deteriorating team performance, cost and schedule overruns, defective deliverables, etc. The project manager is struggling to monitor and control the work and decides to use some of the data analysis techniques to identify the issues and determine the best course of action. How can the project manager use the following techniques to identify the various issues impacting this project? (Drag and drop the items from right to left.) | drag_and_match | {"left_items": ["Corrective actions for better performance", "Corrective actions regarding the cost", "Integrated perspective on project performance", "Identify the main reason for problems", "Forecast performance based on results", "Compare planned and actual performance", "(Not applicable)"], "right_items": ["Business analysis", "Earned value analysis", "Alternatives analysis", "Cost-benefit analysis", "Variance analysis", "Trend analysis", "Root cause analysis"]} | {"matches": {"Corrective actions for better performance": "Alternatives analysis", "Corrective actions regarding the cost": "Cost-benefit analysis", "Integrated perspective on project performance": "Earned value analysis", "Identify the main reason for problems": "Root cause analysis", "Forecast performance based on results": "Trend analysis", "Compare planned and actual performance": "Variance analysis", "(Not applicable)": "Business analysis"}} | 1. People | 1.3 Support team performance | Predictive | While alternatives analysis selects a corrective action or a combination of corrective and preventive actions to implement, cost-benefit analysis determines the best corrective action when it comes to cost factors in a project that deviates from the plan. With earned value analysis, project managers will have a more integrated perspective on scope, schedule, and cost performance. Root cause analysis helps identify the main cause or causes of a problem; with trend analysis, future performance can be forecasted based on past results. The differences between planned and actual performance are reviewed with variance analysis. In contrast, business analysis is not a technique that typically used as part of the Monitor and Control Project Work process implied by the scenario.
32 | Q032 | Due to an uncertain market environment and complexity of upcoming projects, your company is considering a transition from a traditional to hybrid project management approach. The company tasks you with researching various options for incorporating new project management practices that would help the company move closer to its goal. Which of the following would you least likely recommend? | select_one | [{"letter": "A", "text": "Involving business analysts in requirements management"}, {"letter": "B", "text": "Increasing the level of detail during initial project planning"}, {"letter": "C", "text": "Implementing tools to identify complex project elements"}, {"letter": "D", "text": "Incorporating agile, incremental, and iterative practices"}] | {"answer": "B"} | 2. Process | 2.13 Determine appropriate project methodology/methods and practices | Agile / Hybrid | Transitioning an organization from one project management approach to another could be a long and painful process. To reduce the business impact on the organization and decrease the potential stress such a change may cause, the transition should be implemented gradually. This can be achieved by incorporating practices that have proven to be successful. Examples include involving business analysts in requirements management, implementing tools to identify complex project elements, incorporating agile, incremental, and iterative practices, etc. Increasing the level of detail during initial project planning, however, is typical of a traditional project management approach where most of the project planning is done upfront with as many details as possible. Since the organization wants to move away from the traditional project management approach toward a hybrid one, increasing the level of detail during initial project planning would be the least likely option for you to recommend to the organization. AInvolving business analysts in requirements management
33 | Q033 | A project manager hired contractors for a project. Currently, the change control board (CCB) is reviewing a change request to update the communications management plan to include the contractors in all project meetings, events, and celebrations. There is a concern that treating the contractors similar to employees might create a liability to provide employee benefits to contractors. What is the best course of action in this situation? | select_one | [{"letter": "A", "text": "Ask the legal department to provide their insight"}, {"letter": "B", "text": "Deny the request to avoid any liability"}, {"letter": "C", "text": "Approve the request but tell the contractors that participation is voluntary"}, {"letter": "D", "text": "Escalate to the project sponsor"}] | {"answer": "A"} | 3. Business Environment | 3.1 Plan and manage project compliance | Predictive | It cannot be determined from the question if the proposed changes will create a liability for the performing organization to provide employee benefits to the contractors. Expert judgment should be sought to address changes which may have legal implications for procurement. Asking the legal department to provide their insight is an example of expert judgment. Therefore, of the available options, the best course of action is to ask the legal department to provide their insight before approving the request. AAsk the legal department to provide their insight
34 | Q034 | A new product development project went exceptionally well, finishing ahead of schedule and under budget. The project manager is just starting project closure and wants to identify the factors that led to the project's success so that the results can be replicated for future projects. What is the best course of action for the project manager? | select_one | [{"letter": "A", "text": "Perform a regression analysis"}, {"letter": "B", "text": "Review the risk register"}, {"letter": "C", "text": "Measure stakeholder satisfaction"}, {"letter": "D", "text": "Study the project's final report"}] | {"answer": "A"} | 2. Process | 2.17 Plan and manage project/phase closure or transitions | Predictive | It is most likely that a combination of factors was responsible for the remarkable success of the project. The project manager must try to understand if and how multiple actions contributed to the project’s overall success. Regression analysis is an analytical technique where a series of input variables are examined in relation to their corresponding output results in order to develop a mathematical or statistical relationship. For project closure, regression analysis is a technique that analyzes the interrelationships between different project variables that contributed to the project outcomes, which can be used to improve performance on future projects. Therefore, among the available options, performing a regression analysis is the best course of action. APerform a regression analysis
35 | Q035 | You have joined a project in which requirements are elaborated at several intervals during delivery, and the delivery is divided into subsets of the overall product. Change is incorporated at periodic intervals, and risk and cost are controlled by progressively elaborating the plans with new information. Key stakeholders are regularly involved. What development approach is used on your project? | select_one | [{"letter": "A", "text": "Agile"}, {"letter": "B", "text": "Predictive"}, {"letter": "C", "text": "Hybrid"}, {"letter": "D", "text": "Periodic"}] | {"answer": "C"} | 2. Process | 2.13 Determine appropriate project methodology/methods and practices | Agile / Hybrid | Development approach is a component of the project management plan that describes, as the name implies, the approach selected for the development of the product, service, or result delivered by the project. Predictive, iterative, agile, or hybrid are examples of the development approach. The main differences between the various development approaches lie in the way requirements are defined and managed, project deliverables are produced, change is handled, risk and cost are controlled, and stakeholders are involved. The different development approaches can be visually displayed on what is called, the continuum of project life cycles. A predictive development approach is at one extreme of the continuum, while the agile approach is at the other end, with hybrid models being anywhere in between. The scenario describes a project in which requirements are elaborated at several intervals during delivery; the delivery is divided into subsets of the overall product; change is incorporated at periodic intervals; risk and cost are controlled by progressively elaborating the plans with new information; and, key stakeholders are regularly involved. These practices combine elements of both predictive and agile life cycles, making the whole development approach hybrid. Note, the development approach is sometimes called the development life cycle.
36 | Q036 | A number of projects are under consideration for the upcoming quarter. The Director of Global Systems strongly believes that one of the projects, a system upgrade, is needed and aligns with the long-term business strategy. At the executive steering committee meeting scheduled to select projects for the upcoming quarter, what action should the Director take? | select_one | [{"letter": "A", "text": "Advocate for the project with the highest NPV"}, {"letter": "B", "text": "Select a project sponsor"}, {"letter": "C", "text": "Present the merits of the system upgrade project"}, {"letter": "D", "text": "Select a project manager"}] | {"answer": "C"} | 3. Business Environment | 3.2 Evaluate and deliver project benefits and value | Predictive | Projects are selected for many reasons. Not all desired projects can be undertaken by an organization. Decisions as to which projects an organization is to take on are often part of an executive steering committee's responsibility. To get a certain project sponsored and chartered, the Director in this scenario must present the merits and value to the business to the steering committee. Upon selection and approval, the project charter for the project can be commissioned and the project made official. AAdvocate for the project with the highest NPV
37 | Q037 | A project is transitioning to the operations team, and the project manager must outline expectations for the working environment during the knowledge transfer. What should the project manager prioritize in this process? | select_one | [{"letter": "A", "text": "Conduct informal meetings with minimal structure to share lessons learned."}, {"letter": "B", "text": "Ensure a collaborative environment with clear communication and defined roles."}, {"letter": "C", "text": "Assign only the project sponsor to review the knowledge transfer process."}, {"letter": "D", "text": "Rely solely on the knowledge management system for transfer without team interaction."}] | {"answer": "B"} | 2. Process | 2.16 Ensure knowledge transfer for project continuity | Agile / Hybrid | The correct answer is B. A collaborative environment with defined roles ensures that all stakeholders understand their contributions and facilitates effective knowledge transfer. During knowledge transfer, it is essential to establish a structured and collaborative environment to ensure that the receiving team fully understands the processes, tools, and expectations for ongoing operations. Knowledge transfer requires defined roles and responsibilities and active participation from the project and operational teams.
38 | Q038 | During project initiation, the project stakeholders attend a meeting where they discuss how project success should be determined. The majority of the stakeholders are in favor of measuring project success by meeting the metrics of scope, cost, schedule, and quality only. As the project manager, should you agree with this approach? | select_one | [{"letter": "A", "text": "Yes, meeting the metrics of scope, cost, schedule, and quality are the most important criteria for measuring project success."}, {"letter": "B", "text": "No, the measures of project success should be determined after considering all the project objectives."}, {"letter": "C", "text": "Yes, if most of the stakeholders are in favor of a set of success metrics, the project manager should accept the opinion of the majority."}, {"letter": "D", "text": "No, the stated metrics are less important than the level of customer satisfaction, which should be the primary measure of project success."}] | {"answer": "B"} | 2. Process | 2.17 Plan and manage project/phase closure or transitions | Predictive | Traditionally, the project management metrics of project constraints such as scope, schedule, cost, and quality have been the most important factors in defining the success of a project. More recently, practitioners and scholars have determined that the measures of project success should be determined and defined by considering all the project objectives. In addition to the traditional metrics used to determine project success, today's measures of project success should be based on careful consideration of the project benefits management plan, meeting the financial measures such as NPV, ROI, IRR, meeting business case nonfinancial objectives, achieving stakeholder satisfaction, meeting organization's strategy goals and objectives, customer adoption of solutions provided, etc. AYes, meeting the metrics of scope, cost, schedule, and quality are the most important criteria for measuring project success.
39 | Q039 | As a project manager, you are in the initiation stage of a new project. You are currently preparing for a meeting to conduct a benefit analysis with relevant stakeholders to validate project alignment with organizational goals and expected business value. What should the project manager do to prepare for the meeting? | select_one | [{"letter": "A", "text": "Review the project management plan"}, {"letter": "B", "text": "Examine the project business documents"}, {"letter": "C", "text": "Read the stakeholder engagement plan"}, {"letter": "D", "text": "Study the project alignment plan"}] | {"answer": "B"} | 3. Business Environment | 3.2 Evaluate and deliver project benefits and value | Predictive | The project business documents include the business case and benefits management plan which are created as part of pre-project work. The business case is a documented economic feasibility study used to establish the validity of the benefits of a selected component lacking sufficient definition, and that is used as a basis for the authorization of further project management activities. The benefits management plan is the documented explanation defining the processes for creating, maximizing, and sustaining the benefits provided by a project. These documents will contain the relevant information which can be used in preparation for the meeting described by the question. Additionally, with the project in the initiation stage, items described in the other answer choices are not yet available to be used as a source of information. Note that the project charter and stakeholder register are created during project initiation. The question does not state whether or not these documents have already been produced, but they would also provide relevant information for the meeting if they are available. However, the project charter and stakeholder register were not listed as answer choices. AReview the project management plan
40 | Q040 | A project manager is explaining to the stakeholders how the new project will mainly focus on the intangible benefits. To provide a better explanation, the project manager wants to give an example of an intangible benefit. Which of the following is best for the project manager to use as an example? | select_one | [{"letter": "A", "text": "Monetary assets"}, {"letter": "B", "text": "Stockholder equity"}, {"letter": "C", "text": "Market share"}, {"letter": "D", "text": "Brand recognition"}] | {"answer": "D"} | 3. Business Environment | 3.2 Evaluate and deliver project benefits and value | Predictive | The question divides potential benefits of a project into two groups, tangible and intangible. Tangible benefits are those that can be relatively easily expressed in monetary value, for example, anything that results in the production of a material, software, or service adds value to the organization’s assets, increases stockholder equity, and so on. Intangible benefits are those that cannot be directly and easily expressed in monetary value, however, in the long-term can bring value to the organization. Examples of intangible benefits could be brand recognition, public benefit, or trademarks. AMonetary assets
41 | Q041 | Projects in a program are using various project management approaches, such as plan-driven, agile, hybrid. The project teams are complaining that because of that, the team members must enter the same work, hours, risks, and other data in multiple tools. The redundant work is impeding on their productivity time. What is the best course of action for the program manager? | select_one | [{"letter": "A", "text": "Direct the teams to continue entering the data in the various systems"}, {"letter": "B", "text": "Determine what tools and data provide the appropriate oversight"}, {"letter": "C", "text": "Switch all projects in the program to the agile project management approach"}, {"letter": "D", "text": "Pause all data entry until a valuable solution can be determined"}] | {"answer": "B"} | 2. Process | 2.14 Establish project governance structure | Agile / Hybrid | Data and metrics are very important to track, monitor, and control any project. This is true regardless of which project management approach is used. When teams and organizations shift from one approach to another or use various approaches for different projects with a program, it is common for multiple tools and software to be used. The intent of these tools is to assist the teams, stakeholders, and project organizations in managing their data and methodology. However, too many or divergent tools may cause more administration and maintenance. Therefore, project and program governance must determine which data is most relevant and worth the teams' time. The balance between collecting and communicating project data with the resource load to enter and upkeep the data can be difficult, but needed decision. ADirect the teams to continue entering the data in the various systems
42 | Q042 | You and your project team have just completed the development of the project management plan for your agile project. You have requested one of the team members to schedule a meeting to present the finalized project management plan. The team member has asked who should be invited to the meeting. How should you respond? | select_one | [{"letter": "A", "text": "Invite the customer only because it is an agile project"}, {"letter": "B", "text": "Find the answer in the organizational process assets"}, {"letter": "C", "text": "Invite only the project sponsor and the project team"}, {"letter": "D", "text": "Consult the project schedule network diagram"}] | {"answer": "B"} | 2. Process | 2.9 Integrate project planning activities | Agile / Hybrid | In order to obtain approval to proceed with project execution, the project management plan should be presented to the relevant stakeholders according to applicable policies and procedures. The applicable policies and procedures are typically part of the organizational process assets. These documents typically indicate, among other information, the policies and procedures relevant to the activities associated with the approval of the project management plan. By following these policies and procedures, the team member can determine who should be invited to a meeting aimed to review and approve the project management plan. Therefore, of the available choices, researching the organization process assets is the best response. Note, the scenario describes an agile project, yet managed using a project management plan. While this may sound contradicting, there is nothing in the scenario that limits the project to the use of a specific project management methodology with only tools, techniques, artifacts, assets, practices, etc., associated with that methodology. Therefore, it is reasonable to assume that the project as a whole is managed using hybrid methods.
43 | Q043 | As a project manager, you are leading the effort to construct the cellular towers. Another project manager is in charge of building the data center, and yet another project manager is heading up the development of retail distribution. All three of the projects are being managed in a coordinated manner. For which of the following might you be responsible? | select_one | [{"letter": "A", "text": "Assuring benefits realization from the program and component projects"}, {"letter": "B", "text": "Capturing lessons learned, which may benefit other program components"}, {"letter": "C", "text": "Managing interdependencies between program components"}, {"letter": "D", "text": "Managing change requests within a shared governance framework"}] | {"answer": "B"} | 2. Process | 2.12 Manage project artifacts | Predictive | Program components consist of individual projects that are being managed in a coordinated manner. In this case, the three individual projects are components of a program. Program management focuses on the interdependencies between projects to determine the optimal approach for managing them. All the incorrect answer choices represent interdependencies, which must be addressed at the program rather than the project level. Important lessons learned should be captured in the lessons learned register and then transferred to the lessons learned repository. These lessons learned may improve the performance of the current project, other component projects, or future projects. However, the identification and recording of lessons learned is the responsibility of each project manager. Therefore, of the available choices, capturing lessons learned which may benefit other program components is the best answer.
44 | Q044 | You are facilitating a meeting with the customer, team, and key project stakeholders. It becomes evident that requirements are unclear at this point and will frequently change as the project progresses. The customer also mentions that they want the features delivered as the features are completed even if the time between the deliverables will vary from one feature to another. What life cycle would you recommend for the project? | select_one | [{"letter": "A", "text": "Iteration-based agile"}, {"letter": "B", "text": "Flow-based agile"}, {"letter": "C", "text": "Predictive-based agile"}, {"letter": "D", "text": "Any type of agile"}] | {"answer": "B"} | 2. Process | 2.13 Determine appropriate project methodology/methods and practices | Agile / Hybrid | Both approaches, iteration-based agile and flow-based agile, comprises of cycles that deliver completed product increment(s) (feature(s)). Each cycle includes the process of determining requirements, analysis, design, development, and testing. The main difference is that in iteration-based agile, each iteration is of the same length (timebox), and each timebox results in a completed feature(s). In flow-based agile, the time it takes to complete a feature is different for each feature. The team pulls features from the backlog based on the team's capacity to start work. The team defines its workflow with columns on a task board (e.g., a Kanban board) and manages the work in progress for each column. According to the scenario, the customer wants the features delivered as the features are completed even if the time between the deliverables will vary from one feature to another. Therefore, of the choices available, flow-based agile is the best fit for the customer needs and, therefore, the best answer to the question asked. AIteration-based agile
45 | Q045 | As the team completes its third sprint, the company issues a new policy requiring each employee to report their work in the time tracking system. While the policy does not yet specify how detailed the records should be, the management encourages recording as many details as possible. The team members are unsure how to conform to this new policy. What recommendation should the project manager provide to the team? | select_one | [{"letter": "A", "text": "Proceed as before without reporting the work for the sake of delivering value for the project"}, {"letter": "B", "text": "Record as many details as possible to meet the management's request"}, {"letter": "C", "text": "In each sprint, create a user story to cover the time needed to record the work"}, {"letter": "D", "text": "Spend just enough time to conform to the new company policy"}] | {"answer": "D"} | 3. Business Environment | 3.1 Plan and manage project compliance | Agile / Hybrid | Project teams should constantly review the process they use to deliver value for the project. If inefficiencies or waste are found, the team should seek options to adjust the process to improve efficiency and eliminate waste. However, time spent tracking conformance to process is the time lost from delivering value for the project. Therefore, project teams should dedicate just enough time conforming to the process without unnecessarily detracting from the time needed to produce project deliverables. The same goes for the processes and policies the organization puts in place for the project teams to conform to. The new policy requires all employees to report their work in the time tracking system. However, the policy is not specific enough about the level of details needed to be reported. Should the reporting only include the project name? Or should the team members report on specific deliverables they developed, tasks they performed, meetings they attended, calls they made, lunch breaks they took? The management encourages reporting as many details as possible. 'Encourages' is the keyword here. It's not a requirement, not a directive, not a demand. It's just encouragement. Therefore, while some may want to appease the management and report as many details as possible, the recommendation the project manager should make to the team under these circumstances is to spend just enough time to conform to the new company policy so that the negative effect on the value delivered by the team will be minimized. AProceed as before without reporting the work for the sake of delivering value for the project
46 | Q046 | Before you begin project planning, at a high level, you want to ensure a common understanding of the key deliverables among the stakeholders. What is the best way for this to be accomplished? | select_one | [{"letter": "A", "text": "Share the project charter with the stakeholders"}, {"letter": "B", "text": "Email a copy of the project scope statement to the stakeholders"}, {"letter": "C", "text": "Refer the stakeholders to the project management plan"}, {"letter": "D", "text": "Cannot be done yet as stakeholders have not been identified at this point in the project"}] | {"answer": "A"} | 1. People | 1.9 Collaborate with stakeholders | Predictive | The question states that project planning is about to begin which suggests that the processes of the Initiating Process Group have been completed. The Initiating Process Group consists of two project management processes, Develop Project Charter and Identify Stakeholders. Therefore, the project charter and a list of stakeholders are available prior to project planning. At a high level, the project charter ensures a common understanding by the stakeholders of the key deliverables, milestones, and the roles and responsibilities of everyone involved in the project. AShare the project charter with the stakeholders
47 | Q047 | The agile team coach receives an email request for a copy of the project management plan. How should the team coach respond to this request from a stakeholder who is unfamiliar with agile? | select_one | [{"letter": "A", "text": "Send the stakeholder a story map or project roadmap"}, {"letter": "B", "text": "Explain the adaptive planning approach used by agile projects"}, {"letter": "C", "text": "Suggest the stakeholder attend an iteration retrospective and ask their planning questions"}, {"letter": "D", "text": "Ask the product owner to address the stakeholder's questions"}] | {"answer": "B"} | 2. Process | 2.13 Determine appropriate project methodology/methods and practices | Agile / Hybrid | In this situation, the project stakeholder is not familiar with agile methods of planning and has requested for a copy of the project management plan, an artifact, which is typical in traditional, predictive project planning. One of the responsibilities of an agile coach is to educate the organization about agile practices and methodologies. The agile coach should contact the stakeholder and take this opportunity to educate and inform the stakeholder that agile uses adaptive planning rather than predictive planning. The coach can introduce the stakeholder to the product backlog, iterations, releases, iteration and release planning, as well as other planning artifacts such as story maps and product road maps. The coach can then draw parallels between agile artifacts and those used in traditional predictive project management. Introducing key concepts of adaptive planning such as agile discovery and progressive elaboration will help the stakeholder understand agile practices and explain why in agile, a traditional project management plan is not used to plan, monitor and execute the project from start to finish. ASend the stakeholder a story map or project roadmap
48 | Q048 | Due to the worldwide outbreak of a new deadly virus, the World Health Organization (WHO) issues a bid for pharmaceutical companies to develop a vaccine against the virus. The goal is clear - preventing the virus from spreading. The solution, though, is far from being defined. However, once the vaccine is developed, the approval process is very formal and structured. What project management approach is best for this project? | select_one | [{"letter": "A", "text": "Hybrid"}, {"letter": "B", "text": "Agile"}, {"letter": "C", "text": "Predictive"}, {"letter": "D", "text": "Any"}] | {"answer": "A"} | 2. Process | 2.13 Determine appropriate project methodology/methods and practices | Agile / Hybrid | When the goal of the project is clear, but the way to achieve the goal is not, applying one project management approach to the entire project would unlikely result in success. In the scenario provided, the goal is clear - developing a vaccine against the deadly virus and preventing it from spreading across the globe. However, the vaccine itself (the solution to the problem) is obviously unclear since the virus is new, and no vaccine exists, yet. Even those who are not familiar with the specifics of the pharmaceutical industry understand that a lot of experimentation will be required to develop the vaccine. Under these circumstances, most of the project aspects, including the vaccine approval process, can be managed using the predictive project management approach. However, the development phase of the vaccine will be better off with agile methods, allowing short development cycles, testing, early feedback, and adaptation. The combination of the predictive and agile project management approaches will result in a hybrid project.
49 | Q049 | As a project manager, you want to establish a culture of continuous improvement with your project team, so you encourage the team to look for and implement small incremental improvements in the development process. Which of the following are you recommending to the team? | select_one | [{"letter": "A", "text": "Kaikaku"}, {"letter": "B", "text": "Decomposition"}, {"letter": "C", "text": "Ishikawa"}, {"letter": "D", "text": "Kaizen"}] | {"answer": "D"} | 2. Process | 2.7 Plan and manage quality of products/deliverables | Predictive | Kaizen is the Japanese word for improvement. A kaizen approach makes incremental change through small steps, thereby establishing a process of continuous improvement. By applying kaizen, a development team can optimize efficiency and quality. The kaizen approach would establish a continuous improvement process by encouraging the development team to look for and implement small incremental improvements in the development process. The topic of this question is only briefly mentioned in thePMBOK®Guide. However, the Project Management Professional (PMP)®Examination Content Outline (ECO) indicates that while there are some commonalities between thePMBOK®Guideand the ECO, the exam is not bound by thePMBOK®Guide. The list of enablers specified in the tasks of the ECO domains is not exhaustive either. The ECO assumes that prospective PMP aspirants are familiar with other sources of information/preparation, including but not limited to the PMI Code of Ethics and Professional Conduct, PMI's Practice Standards (e.g., Scheduling, Earned Value Management, etc.), commonly frowned upon project management practices, such as gold plating, and others. We intentionally have these questions in our simulator so that you would be better prepared for the real exam. PMP aspirants are encouraged to explore additional sources of information and/or to be familiar with them from their project management experience.